## product backlog
Product Backlog Id	Priority	User Story Id	User story	Scrum team assign	Status	Remark
1	High	User001	User Registration	Hitesh	Complete	NA
2	Low	User002	Notification	Kumar jd	Not Started	1 Hour dealy
3	Low	User003	Cart	Jaswanth	Progress	NA
4	Medium	User004	Reset Password	Apurva Shinde	Complete	NA
5	High	User005	Hotel Search	Amar Kolhe	Complete	NA
6	High	User006	Payment	Anusha Bharath	Complete	NA
7	Medium	User007	Address mgmt	Bhavani	Progress	NA
8	High	User008	Rewards	Atin	Complete	NA
9	High	User009	Photographs	Ashish	Progress	Wating for Photos
10	Medium	User010	Reviews	Aravind Naidu	Progress	NA
11	High	User011	User Login	Dipti	Complete	NA

## sprint backlog 1
User story id	User story name	User story step defination		Assigned to	Estimated time	Actual time	Acceptance Criteria	Status	Remarks
User001	User Registration	As a user I can provide my email id, phone no., password, username, gender, DOB for registration / After successful registration as a user I am navigated to the home screen		Hitesh	3 hours	3 hours	Search results include hotels matching the destination	Complete	NA

User005	Hotel Search	As a Traveler, I want to Select the catagories .		Amar kolhe	5 hour	3 hour		Complete	NA
User006	Payment	As a Traveler, I want to Select the date.		Anusha Bharath	1 hour	1 hour		Complete	NA

## sprint backlog 2
User story id User story name User story step defination Assigned to Estimated time Actual time Acceptance Criteria Status Remarks

User002	Notification	As a Traveler, I want to find available options for my hotel	Kumar jd		1 hour	1 hour	Filters allow narrowing results by price, rating, amenities	Not started	1 Hour delay
User003	Cart	As a Traveler , I want to view detailed information about each hotel,	Jaswanth		4 hour	4 hour	display key information like hotel name, photos, price,	Progress	NA
User004	Reset Password	As a Traveler, I want to view including photos, amenities, and reviews	Apurva shinde		7 hour	4 hour		Complete	NA

## sprint backlog 3
User story id	User story name	User story step defination		Assigned to	Estimated time	Actual time	Acceptance Criteria	Status	Remarks

User007	Address mgmt	As a Traveler, I want to book the room.		Bhavani	4 hour	3 hour		Progress	NA
User008	Rewards	As a Traveler, I want to payment option.		Atin	5 hour	4 hour		Complete	NA
User009	Photographs	As a Traveler, I want to notify about booking .		Ashish	4 hour	3 hour		Progress	Waiting for photos
User010	Reviews	As a Traveler, I want to confirm my room booking.		Aravind Naidu	3 hour	2 hour		Progress	NA
User011	User Login	As a Traveler, I want to logout .			3 hour	2 hour		Complete	NA

## Kanban
TODO	In Progress					Completed
		Design	Develop	Test	Deploy
User story	done	done	done	done	done	Complete
User Registration	done	done	done	done	done	Complete
Notification	done	done	done		done	Complete
Cart	done	done	done	done	done
Reset Password	done	done	done	done	done	Complete
Hotel Search	done	done	done	done	done	Complete
Payment	done	done		done	done	Complete
Address mgmt	done	done	done	done	done	Complete
Rewards	done	done	done	done	done	complete
Photographs	done	done	done		done	Complete
Reviews	done	done	done		done
User Login	done	done	done	done	done	Complete

## Defact Tracking
Defect id	Defect	Created On	Creater	Assign to	Serverity	priority	status
doo1	Login Function is not Working	18-June	Aravind Naidu	Dipti	medium	high	close
doo2	Can not able to search hotel by neaarby location	19-June	Apurva Shinde	Amar Kolhe	high	medium	close
doo3	User is not able to pay with the debit card	19-June	Hitesh	Anusha Bharath	medium	low	open
doo4	Issue in selecting the category	20-June	Ashish	Jaswanth	low	high	close
doo5	Address is wrong	20-June	Kumar jd	Bhavani	medium	low	open